FOODO AFRICA

Restaurant Platform

Scrum Master Sprint Plan & Delivery Guide

MVP Development Program

20 July 2026 – 28 August 2026

| Document Title | Foodo Africa Restaurant Platform — Scrum Master Sprint Plan |
| --- | --- |
| Project | Foodo Africa Restaurant Super App (MVP) |
| Prepared By | Scrum Master |
| Version | 1.0 |
| Date | 17 July 2026 |
| Project Duration | 20 July 2026 – 28 August 2026 (6 Sprints) |
| Methodology | Scrum |
| Status | Approved for Execution |

# 1. Introduction & Purpose

This document serves as the Scrum Master's master sprint plan for the Foodo Africa Restaurant Platform MVP. It translates the product vision into a structured, six-sprint delivery plan and defines the Scrum framework — roles, ceremonies, and cadence — that will govern how the team plans, builds, and reviews work.

The goal of the program is to design, build, and launch a market-ready Minimum Viable Product (MVP) of the Foodo Africa Restaurant Super App: a platform that lets restaurant owners, managers, and cashiers manage user accounts, menus, inventory, point-of-sale transactions, suppliers, and business insights — including offline operation for low-connectivity environments.

## 1.1 Project Snapshot

- Duration: 6 sprints, 20 July 2026 – 28 August 2026

- Sprint length: 5 working days (Monday–Friday)

- Methodology: Scrum

- Final deliverable: MVP released to pilot restaurants on 28 August 2026

# 2. Scrum Framework Overview

The team will operate in fixed, one-week sprints. Each sprint begins with Sprint Planning on Monday morning and closes with a Sprint Review and Retrospective on Friday afternoon, giving the Product Owner and stakeholders a working increment to inspect every week.

## 2.1 Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Scrum Master | Facilitates all Scrum ceremonies, removes impediments, protects the team from scope disruption, tracks sprint health, and ensures the team adheres to Scrum values and cadence. |
| Product Owner | Owns and prioritizes the Product Backlog, defines acceptance criteria, represents restaurant-owner and cashier stakeholder needs, and approves each Sprint Review deliverable. |
| Development Team | Cross-functional engineers (front-end, back-end, QA) who design, build, test, and deliver a potentially shippable increment each sprint. |
| Stakeholders | Pilot restaurant owners, managers, and cashiers who provide feedback at Sprint Reviews and validate real-world usability. |

## 2.2 Scrum Ceremonies & Cadence

| Ceremony | Cadence | Purpose |
| --- | --- | --- |
| Sprint Planning | Day 1 of each sprint (Monday AM) | Define the Sprint Goal and select backlog items for the sprint. |
| Daily Standup | Daily, 15 minutes | Sync on progress, plans for the day, and blockers. |
| Backlog Refinement | Mid-sprint (Wednesday) | Clarify and estimate upcoming backlog items for the next sprint. |
| Sprint Review | Day 5 of each sprint (Friday PM) | Demo the working increment to the Product Owner and stakeholders; gather feedback. |
| Sprint Retrospective | Day 5 of each sprint (Friday PM) | Reflect on what went well, what didn't, and agree on improvement actions. |

## 2.3 Scrum Artifacts

- Product Backlog — the single, prioritized source of all features and requirements, owned by the Product Owner.

- Sprint Backlog — the subset of backlog items and daily tasks committed to for the current sprint (detailed in Section 4).

- Increment — the sum of completed, "Done" work at the end of each sprint, demonstrated at Sprint Review.

# 3. Sprint Roadmap Overview

The MVP is delivered across six thematic sprints, each building on the previous one, moving from foundational user management through to a fully tested, market-ready launch.

| Sprint | Dates | Theme | Key Deliverables |
| --- | --- | --- | --- |
| Sprint 1 | 20–24 Jul 2026 | Project Foundation & User Management | Registration, login, user roles, restaurant profiles, dashboard shell. |
| Sprint 2 | 27–31 Jul 2026 | Product & Inventory Foundation | Digital menu, product categories, stock tracking, low-stock alerts. |
| Sprint 3 | 3–7 Aug 2026 | POS & Sales Management | Order creation, payment processing, sales history and reporting. |
| Sprint 4 | 10–14 Aug 2026 | Offline Capability & Remote Monitoring | Offline sales, data sync, owner remote dashboard. |
| Sprint 5 | 17–21 Aug 2026 | Suppliers & AI Assistant | Supplier management, purchasing workflow, AI-powered business insights. |
| Sprint 6 | 24–28 Aug 2026 | Testing, Market Preparation & Launch | End-to-end QA, UX polish, pilot onboarding, production launch. |

# 4. Definition of Done

A backlog item is only considered complete when it meets all of the following criteria. This standard applies uniformly across all six sprints and protects the integrity of each weekly increment.

- Code is written, peer-reviewed, and merged to the main branch.

- Feature meets its acceptance criteria as defined by the Product Owner.

- Unit and functional tests pass; no critical or high-severity bugs remain open.

- Feature is tested on at least one low-connectivity / offline scenario where applicable.

- UI is responsive and reviewed for usability by at least one team member outside the author.

- Relevant documentation (API notes, user-facing help text) is updated.

- Feature is deployed to the staging environment and demonstrated at Sprint Review.

# 5. Detailed Sprint Plans

The following sections break each sprint down into daily activities, tasks, and expected outcomes, providing the team with a day-by-day execution guide.

# Sprint 1: Project Foundation & User Management

Dates: 20 – 24 July 2026

Sprint Goal: Establish the technical foundation of the platform and enable restaurant owners, managers, and cashiers to register, log in, and set up their restaurant profile.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 20 Jul | Project Setup & Planning | Review MVP scope; define user journeys; prepare dev environment and project structure; define initial database and business requirements. | Team aligned on the MVP vision and development plan. |
| Tue, 21 Jul | User Account System | Implement registration and login; create user profiles; define roles (Owner, Manager, Cashier). | Users can create accounts and access the platform. |
| Wed, 22 Jul | Restaurant Profile Management | Build restaurant registration; capture name, location, contact and business details; link users to restaurants. | Restaurant owners can create their business profile. |
| Thu, 23 Jul | Application Structure & Dashboard | Build main app layout and dashboard structure; add navigation; scaffold Sales, Inventory, Products, Suppliers, Reports sections. | Users have a clear platform interface. |
| Fri, 24 Jul | Sprint Review & Retrospective | Test registration and login; review completed features; fix issues; collect team feedback; prepare Sprint 2 backlog. | User management foundation completed. |

# Sprint 2: Product & Inventory Foundation

Dates: 27 – 31 July 2026

Sprint Goal: Give restaurants the ability to build a digital menu and track stock levels in real time.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 27 Jul | Product Management Planning | Define product data structure; create product categories; design the product management workflow. | Product management plan completed. |
| Tue, 28 Jul | Product Creation Features | Add new products, categories, and pricing; enable updates to product details. | Restaurants can create their digital menu. |
| Wed, 29 Jul | Inventory Setup | Add stock management; record available quantities; track stock changes. | Restaurants can see their available stock. |
| Thu, 30 Jul | Inventory Improvement | Add stock updates and stock history; build low-stock identification. | Restaurant owners can monitor inventory status. |
| Fri, 31 Jul | Sprint Review & Testing | Test product management and inventory operations; fix issues; prepare POS requirements. | Product and inventory module completed. |

# Sprint 3: POS & Sales Management

Dates: 3 – 7 August 2026

Sprint Goal: Deliver a working point-of-sale flow that lets cashiers take orders, accept payment, and lets owners review sales.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 3 Aug | POS Design & Order Flow | Define sales workflow; design cashier experience; prepare the ordering process. | POS workflow ready. |
| Tue, 4 Aug | Order Processing | Create customer orders; add products to orders; calculate totals; apply discounts. | Cashiers can create orders. |
| Wed, 5 Aug | Payment Management | Add payment methods (cash, mobile money, credit); record completed payments. | Restaurant can complete sales transactions. |
| Thu, 6 Aug | Sales Reporting | Create sales history; add daily sales summary; track transactions. | Owners can review business sales. |
| Fri, 7 Aug | POS Testing & Review | Test the complete sales workflow; improve cashier experience; fix issues. | POS system ready for restaurant operations. |

# Sprint 4: Offline Capability & Remote Monitoring

Dates: 10 – 14 August 2026

Sprint Goal: Ensure restaurants can keep operating without internet access and give owners remote visibility into their business.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 10 Aug | Offline Operation Planning | Identify critical offline features; define data synchronization requirements; prepare the offline workflow. | Offline strategy completed. |
| Tue, 11 Aug | Offline Sales Capability | Enable sales recording without internet; store temporary business data; test offline transactions. | Restaurant can continue selling without internet. |
| Wed, 12 Aug | Data Synchronization | Synchronize offline records once connectivity returns; ensure data consistency; test the sync process. | Offline and online data work together. |
| Thu, 13 Aug | Owner Remote Dashboard | Build owner monitoring view showing sales, orders, inventory status, and business performance. | Owners can monitor businesses remotely. |
| Fri, 14 Aug | Sprint Review & Testing | Test offline operations and remote monitoring; fix issues. | Offline and monitoring features completed. |

# Sprint 5: Suppliers & AI Assistant

Dates: 17 – 21 August 2026

Sprint Goal: Digitize the supplier and purchasing workflow and introduce an AI assistant that surfaces actionable business insights.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 17 Aug | Supplier Management | Create supplier records; capture supplier information; connect restaurants with suppliers. | Restaurants can manage supplier information. |
| Tue, 18 Aug | Purchase Management | Create purchase requests; record purchases; update inventory after purchases. | Restaurant purchasing process is digital. |
| Wed, 19 Aug | AI Business Assistant Setup | Define AI use cases; prepare sample business questions; connect the AI assistant to business data. | AI assistant foundation completed. |
| Thu, 20 Aug | AI Business Insights | Enable AI-generated answers on sales analysis, product performance, and stock recommendations. | Owners receive intelligent business insights. |
| Fri, 21 Aug | Sprint Review | Test supplier features and the AI assistant; improve user experience. | Supplier and AI modules completed. |

# Sprint 6: Testing, Market Preparation & Launch

Dates: 24 – 28 August 2026

Sprint Goal: Harden the full system, prepare pilot restaurants for onboarding, and launch the MVP into market testing.

| Date | Focus | Key Tasks | Expected Outcome |
| --- | --- | --- | --- |
| Mon, 24 Aug | Complete System Testing | Test the full restaurant workflow, all user roles, and the sales/inventory process end to end. | System works from registration to daily operations. |
| Tue, 25 Aug | User Experience Improvement | Improve the interface; fix usability issues; improve performance. | Application becomes easier for restaurant users. |
| Wed, 26 Aug | Pilot Preparation | Prepare demo accounts, training materials, and the onboarding process. | Ready for first restaurant users. |
| Thu, 27 Aug | Final Review & Deployment Prep | Final testing; security review; production preparation; confirm MVP readiness. | MVP ready for launch. |
| Fri, 28 Aug | MVP Launch & Market Testing | Release MVP to pilot restaurants; collect initial feedback; monitor usage; prepare improvement roadmap. | Oryon Foods Restaurant MVP officially enters market testing. |

# 6. Risk Management

The Scrum Master will maintain and review the following risk register at each Sprint Retrospective, updating impact levels and mitigation status as the project progresses.

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Unreliable internet connectivity in pilot restaurants | High | Prioritize offline-first architecture in Sprint 4; test sync thoroughly before launch. |
| Scope creep from stakeholder feedback mid-sprint | Medium | Product Owner filters all new requests into the backlog for future sprint planning, not the active sprint. |
| Payment integration delays (mobile money providers) | Medium | Begin technical discovery and sandbox access requests in Sprint 2, ahead of Sprint 3 build. |
| AI assistant accuracy / relevance of insights | Medium | Validate AI use cases with real sales data early in Sprint 5; keep scope to defined insight categories. |
| Tight 6-sprint timeline for a full-featured MVP | High | Maintain strict backlog prioritization; defer non-critical features to a post-MVP roadmap. |
| User adoption resistance from cashiers/owners unfamiliar with digital tools | Medium | Build training materials and a simple onboarding flow in Sprint 6; run a guided pilot. |

# 7. Success Metrics & Sprint Health Tracking

The Scrum Master will track the following metrics throughout the program to monitor delivery health and inform continuous improvement.

| Metric | Description |
| --- | --- |
| Sprint Velocity | Story points / activities completed vs. planned, tracked each sprint to establish a stable delivery baseline. |
| Sprint Goal Success Rate | % of sprints where the committed Sprint Goal is fully achieved by Friday review. |
| Defect Escape Rate | Number of bugs found after a feature is marked "Done", tracked per sprint. |
| Stakeholder Satisfaction | Qualitative feedback score collected at each Sprint Review from pilot users and the Product Owner. |
| Pilot Adoption (Sprint 6) | Number of pilot restaurants actively using the platform daily during market testing. |

# 8. MVP Delivery

Final MVP Delivery Date: Friday, 28 August 2026.

At the close of Sprint 6, Oryon Foods will have a working restaurant platform — covering user management, product and inventory control, point-of-sale operations, offline capability, supplier management, and AI-powered business insights — ready for real restaurants to use, with a feedback loop in place to guide the post-MVP roadmap.